## Project Cost Tracker
EXHIBIT II-1
PROJECT LEDGER CARD
[5 empty] | START DATE: |  | 2013-09-20
[5 empty] | END DATE: |  | 2013-10-31
MAIN STREET SCHOOL DISTRICT
Building Expansion Project | Main Street School Remodel |  |  |  | Project Code:
Project Manager: Sanders
|  |  | RATE | UNIT | HOURS | TOTAL | GRAND TOTAL
Direct Costs - Labor
|  | Maintenance Worker I | 15 | HR | 60 | 60 | 900
|  | Maintenance Worker II | 17.5 | HR | 90 | 90 | 1575
|  | Foreman / Job Superintendent | 40 | HR | 40 | 40 | 1600
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
|  | Total Hours |  |  | 190 | 190
|  | T & L Expenses |  |  |  |  | 4075
|  | Overhead |  |  |  | 30% | 1222.5
|  | Labor w/Overhead |  |  |  |  | 5297.5
|  | Direct Costs - Equipment | RATE | UNIT | QTY | TOTAL | GRAND TOTAL
|  | Flatbed Truck - Daily | 38.8 | DY | 2 | 2 | 77.6
|  | Table Saw, 16” Blade - Weekly | 102.46 | WK | 1 | 1 | 102.46
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  | Total Hours |  |  | 3 | 3
|  | Total Equipment Charges |  |  |  |  | 180.06
|  | Overhead |  |  |  | 30% | 54.018
|  | Total Equipment w/Overhead |  |  |  |  | 234.078
|  | Materials/Supplies/Subcontracts | RATE | UNIT | QTY | TOTAL | GRAND TOTAL
|  | Carpeting | 2 | SF | 400 | 400 | 800
|  | Painting-Subcontract | 1500 | EA | 1 | 1 | 1500
|  | Drywall | 50 | EA | 10 | 10 | 500
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  | Total Hours |  |  | 411 | 411
|  | Total Materials/Supplies/Subcontracts |  |  |  |  | 2800
|  | Overhead |  |  |  | 30% | 840
|  | Total Materials/Supplies/Subcontracts w/Overhead |  |  |  | 0 | 3640
|  | TOTAL PROJECT COST |  |  |  |  | 9171.578

## Week Version
EXHIBIT II-1
PROJECT LEDGER CARD
[8 empty] | START DATE: |  | 2013-09-20
[8 empty] | END DATE: |  | 2013-10-31
MAIN STREET SCHOOL DISTRICT
Building Expansion Project | Main Street School Remodel | [6 empty] | Project Code:
Project Manager: Sanders
|  |  | RATE | UNIT | HOURS |  |  |  | TOTAL | GRAND TOTAL
|  | Direct Costs - Labor |  |  | Week 1 | Week 2 | Week 3 | Week 4
|  | Maintenance Worker I | 20 | HR | 20 | 40 | 20 | 20 | 100 | 2000
|  | Maintenance Worker II | 17.5 | HR | 20 | 15 | 20 | 10 | 65 | 1137.5
|  | Foreman / Job Superintendent | 40 | HR | 20 | 20 | 20 | 20 | 80 | 3200
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
|  | Total Hours | [5 empty] | 50 | 190
|  | T & L Expenses | [7 empty] | 6337.5
|  | Overhead | [6 empty] | 30% | 1901.25
|  | Labor w/Overhead | [7 empty] | 8238.75
|  | Direct Costs - Equipment | RATE | UNIT | QTY | TOTAL | GRAND TOTAL
|  | Flatbed Truck - Daily | 38.8 | DY | 4 | 2 | 155.2
|  | Table Saw, 16” Blade - Weekly | 102.46 | WK | 3 | 1 | 307.38
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  | Total Hours |  |  | 7 | 3
|  | Total Equipment Charges |  |  |  |  | 462.58
|  | Overhead |  |  |  | 30% | 138.774
|  | Total Equipment w/Overhead |  |  |  |  | 601.354
|  | Materials/Supplies/Subcontracts | RATE | UNIT | QTY | TOTAL | GRAND TOTAL
|  | Carpeting | 2 | SF | 400 | 400 | 800
|  | Painting-Subcontract | 1500 | EA | 1 | 1 | 1500
|  | Drywall | 50 | EA | 10 | 10 | 500
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  | Total Hours |  |  | 411 | 411
|  | Total Materials/Supplies/Subcontracts |  |  |  |  | 2800
|  | Overhead |  |  |  | 30% | 840
|  | Total Materials/Supplies/Subcontracts w/Overhead |  |  |  | 0 | 3640
|  | TOTAL PROJECT COST |  |  |  |  | 12480.104